## Sheet1
Timetable
Week | Date | Day | What | Who
38 | 2020-09-15 | Tu | Preparation Kickoff Meeting | PT | PT | Projekt Team
| 2020-09-16 | We | Kickoff Meeting | PT S | PT S | Projekt Team with Supervisors
39 | - | - | Further information gathering on MTD, RL, Networksec | PT
| 2020-09-23 | We | Weekly Meeting | PT S
40 | - | - | Further information gathering on MTD, RL, Networksec | PT | Meetings
| - | - | Start writing PA, table of contents and structure | PT | PA Paper
| 2020-09-30 | We | Weekly Meeting | PT S | Research
41 | - | - | Further information gathering on MTD, RL, Networksec | PT | "Coding"
| - | - | Paper: Sota and goal | PT
| 2020-10-07 | We | Weekly Meeting | PT S
42 | - | - | Create general Use-Cases | PT
| - | - | Paper: Theoretical foundations | PT
| 2020-10-14 | We | Weekly Meeting | PT S
43 | - | - | Search and examine tools / frameworks | PT
| - | - | Paper: Reviewing & Correcting | PT
| 2020-10-21 | We | Weekly Meeting | PT S
44 | - | - | Search and examine tools / frameworks | PT
| - | - | Paper: Reviewing & Correcting | PT
| 2020-10-28 | We | Weekly Meeting | PT S
45 | - | - | implement experiment
| - | - | Paper: Methods | PT
| 2020-11-04 | We | Weekly Meeting | PT S
46 | - | - | implement experiment
| - | - | Paper: Methods | PT
| 2020-11-11 | We | Weekly Meeting | PT S
47 | - | - | implement experiment
| - | - | Paper: Results | PT
| 2020-11-18 | We | Weekly Meeting | PT S
48 | - | - | experient with tools / frameworks and evaluate outcome / fitnes of methods
| - | - | Paper: Discussion | PT
| 2020-11-25 | We | Weekly Meeting | PT S
49 | - | - | documentation of tools & frameworks
| - | - | Hand in Paper for Feedback | PT S
| - | - | Paper: Reviewing & Correcting | PT
| 2020-12-02 | We | Weekly Meeting | PT S
50 | - | - | documentation of tools & frameworks
| - | - | Paper: Reviewing & Correcting | PT
| 2020-12-09 | We | Weekly Meeting | PT S
51 | - | - | Reserve
| 2020-12-19 | Sa | Abgabe PA | Team