## Sheet1
Timetable
Week | Date | Day | What | Who
38 | 2020-09-15 | Tu | Preparation Kickoff Meeting | PT | PT | Projekt Team
| 2020-09-16 | We | Kickoff Meeting | PT B | PT B | Projekt Team with Supervisors
39 | 2020-09-23 | We | Weekly Meeting | PT B
| - | - | Further information gathering on MTD, RL, Networksec | PT | Meetings
40 | - | - | Start writing PA, table of contents and structure | PT | PA Report
| 2020-09-30 | We | Weekly Meeting | PT B | Research
41 | - | - | Further information gathering on MTD, RL, Networksec | PT | Coding
| - | - | Stoa and goal | PT
| 2020-10-07 | We | Weekly Meeting | PT B
42 | - | - | Create general Use-Cases | PT
| - | - | Theoretical foundations | PT
| 2020-10-14 | We | Weekly Meeting | PT B
43 | - | - | Search and examine tools / frameworks | PT
| - | - | Reviewing & Correcting | PT
| 2020-10-21 | We | Weekly Meeting | PT B
44 | - | - | Search and examine tools / frameworks | PT
| - | - | Reviewing & Correcting | PT
| 2020-10-28 | We | Weekly Meeting | PT B
45 | - | - | sort out surveys / studies | PT
| - | - | Methods | PT
| 2020-11-04 | We | Weekly Meeting | PT B
46 | - | - | sort out surveys / studies | PT
| - | - | Methods | PT
| 2020-11-11 | We | Weekly Meeting | PT B
47 | - | - | sort out Use-Cases & tools
| - | - | Results | PT
| 2020-11-18 | We | Weekly Meeting | PT B
48 | - | - | implement tools / frameworks?
| - | - | Discussion | PT
| 2020-11-25 | We | Weekly Meeting | PT B
49 | - | - | implement tools / frameworks?
| - | - | Sources | PT
| 2020-12-02 | We | Weekly Meeting | PT B
50 | - | - | documentation of tools & frameworks
| - | - | Reviewing & Correcting | PT
| 2020-12-09 | We | Weekly Meeting | PT B
51 | - | - | Reserve
| 2020-12-19 | Sa | Abgabe PA | Team